## summary
FEATURES
Feature Status | Count of STATUS
Close | 38
In Progress | 0
Not Started | 0
TESTCASE
Tesrcase Status | Count of STATUS
Close | 8
In Progress | 0
Not Started | 0
COVERAGE
Coverage Status | Count of STATUS
Close | 10
In Progress | 0
Not Started | 0

## features_extraction
FEATURE ID | FEATURE | DESCRIPTION | Device Type (apb_mas_drv,apb_mas_mon,Interface) | IMPLEMENTATION TYPE (apb_assertions, apb_mas_mon, apb_mas_drv) | PRIORITY (P1, P2, P3) | IMPLEMENTATION DETAILS | TEST NAME | COMMENTS | Status | Effort | Remaining Effort
APB_RST_01 | Reset Assertion | Verify APB interface signals are driven to default values during reset assertion | apb_mas_drv, Interface | apb_mas_drv | P1 | apb_mas_drv drives PSEL, PENABLE, PWRITE to default values during reset | apb_reset_test | Reset protocol validation | CLOSE | 1 | CLOSE
APB_RST_02 | Reset Deassertion | Verify protocol operation resumes correctly after reset deassertion | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P1 | apb_mas_mon validates protocol activity after reset release | apb_reset_test | Post-reset operation check | CLOSE | 1 | CLOSE
APB_RST_03 | apb_mas_drv Reset Handling | Verify apb_mas_drv FSM transitions to IDLE state during reset | apb_mas_drv | apb_mas_drv | P1 | apb_mas_drv FSM forced to IDLE state whenever reset asserted | apb_reset_test | FSM reset validation | CLOSE | 0.8 | CLOSE
APB_RST_04 | DUT Reset Initialization | Verify slave internal registers/memory initialized after reset | apb_mas_mon, apb_assertions | apb_assertions | P1 | apb_scoreboard verifies default DUT output values after reset | apb_reset_test | DUT initialization validation | CLOSE | 0.7 | CLOSE
APB_WR_01 | APB Write Setup Phase | Verify valid APB write setup phase generation | apb_mas_drv, Interface | apb_mas_drv | P1 | apb_mas_drv asserts PSEL with valid address/data during setup phase | apb_sanity_test | Setup phase validation | CLOSE | 1 | CLOSE
APB_WR_02 | APB Write Access Phase | Verify PENABLE assertion during write access phase | apb_mas_drv, Interface | apb_mas_drv | P1 | apb_mas_drv asserts PENABLE in access phase as per APB protocol | apb_sanity_test | Access phase validation | CLOSE | 1 | CLOSE
APB_WR_03 | APB Write Completion | Verify write transfer completes only when PREADY asserted | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P1 | apb_mas_drv waits until PREADY goes high before completing transfer | apb_sanity_test | Handshake validation | CLOSE | 0.85 | CLOSE
APB_WR_04 | Write Address Handling | Verify correct address propagation during write transfer | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P1 | apb_mas_mon samples address and compares against generated transaction | apb_sanity_test | Address integrity check | CLOSE | 1 | CLOSE
APB_WR_05 | Write Data Handling | Verify correct write data transfer | apb_mas_drv, apb_mas_mon, apb_assertions | apb_mas_drv, apb_mas_mon, apb_assertions | P1 | apb_scoreboard compares expected and actual write transaction data | apb_sanity_test | Data integrity validation | CLOSE | 0.75 | CLOSE
APB_WR_06 | Write Strobe Support | Verify write strobe (PSTRB) byte-lane configuration updates memory correctly | apb_mas_drv, Interface | apb_mas_drv | P1 | apb_mas_drv drives PSTRB and memory masking is applied based on active strobe bytes | apb_sanity_test | Write strobe validation | CLOSE | 0.5 | CLOSE
APB_WR_07 | Strobe Stability | Verify write strobe remains stable during wait states | apb_mas_mon, apb_assertions | apb_assertions | P1 | Assertion verifies PSTRB remains stable during active write wait states | apb_sanity_test | Strobe stability validation | CLOSE | 0.5 | CLOSE
APB_RD_01 | APB Read Setup Phase | Verify valid APB read setup phase generation | apb_mas_drv, Interface | apb_mas_drv | P1 | apb_mas_drv initiates read transfer with proper control signals | apb_sanity_test | Read setup validation | CLOSE | 1 | CLOSE
APB_RD_02 | APB Read Access Phase | Verify APB read access phase sequencing | apb_mas_drv, Interface | apb_mas_drv | P1 | PENABLE asserted during read access cycle | apb_sanity_test | Read access validation | CLOSE | 1 | CLOSE
APB_RD_03 | Read Data Sampling | Verify PRDATA sampled correctly by apb_mas_mon | apb_mas_mon | apb_mas_mon | P1 | apb_mas_mon captures PRDATA only when transfer completes | apb_sanity_test | Read data sampling validation | CLOSE | 0.75 | CLOSE
APB_RD_04 | Read Completion | Verify read transfer completes only on PREADY assertion | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P1 | apb_mas_drv and apb_mas_mon synchronize transaction completion with PREADY | apb_sanity_test | Read handshake validation | CLOSE | 0.8 | CLOSE
APB_WAIT_01 | Wait State Insertion | Verify slave inserts wait states using PREADY low | apb_mas_mon, Interface | apb_mas_mon | P1 | apb_mas_mon detects extended access phase while PREADY low | apb_random_test | Wait-state validation | CLOSE | 0.6 | CLOSE
APB_WAIT_02 | Wait State Hold | Verify address/control/data stability during wait states | apb_mas_mon, apb_assertions | apb_mas_mon, apb_assertions | P1 | apb_assertions verifies signals remain stable until transfer completion | apb_random_test | Stability check | CLOSE | 0.55 | CLOSE
APB_WAIT_03 | Delayed Transfer Completion | Verify transaction completes after delayed PREADY assertion | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P1 | apb_mas_drv holds transaction active until slave ready | apb_random_test | Delayed completion validation | CLOSE | 0.6 | CLOSE
APB_B2B_01 | Back-to-Back Write | Verify consecutive write transfers without idle cycle | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P2 | apb_mas_drv issues sequential write transfers continuously | apb_transition_test | Throughput validation | CLOSE | 0 | CLOSE
APB_B2B_02 | Back-to-Back Read | Verify consecutive read transfers without idle cycle | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P2 | apb_mas_mon reconstructs continuous read operations correctly | apb_transition_test | Continuous read validation | CLOSE | 0 | CLOSE
APB_B2B_03 | Write-to-Read Transition | Verify seamless write-to-read transfer transition | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P2 | apb_mas_drv transitions protocol control between write and read operations | apb_transition_test | Transition validation | CLOSE | 0 | CLOSE
APB_B2B_04 | Read-to-Write Transition | Verify seamless read-to-write transfer transition | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P2 | Consecutive mixed-direction transfers verified | apb_transition_test | Mixed transaction validation | CLOSE | 0 | CLOSE
APB_ERR_01 | PSLVERR Assertion | Verify slave error response generation | apb_mas_mon, Interface | apb_mas_mon | P2 | apb_mas_mon samples PSLVERR during erroneous transaction | apb_error_test | Error response validation | CLOSE | 0 | CLOSE
APB_ERR_02 | Error Sampling | Verify apb_mas_mon captures PSLVERR correctly | apb_mas_mon | apb_mas_mon | P2 | Error response propagated into transaction object | apb_error_test | Error apb_mas_moning validation | CLOSE | 0 | CLOSE
APB_MON_01 | Transaction Capture | Verify apb_mas_mon reconstructs APB transaction correctly | apb_mas_mon | apb_mas_mon | P1 | apb_mas_mon converts pin-level activity into transaction object | apb_sanity_test | apb_mas_mon validation | CLOSE | 1 | CLOSE
APB_MON_02 | Wait-State apb_mas_moning | Verify apb_mas_mon handles extended access phase correctly | apb_mas_mon | apb_mas_mon | P1 | apb_mas_mon waits for PREADY before transaction completion | apb_random_test | Extended access apb_mas_moning | CLOSE | 0.7 | CLOSE
APB_MON_03 | Read Data Collection | Verify apb_mas_mon captures PRDATA accurately | apb_mas_mon | apb_mas_mon | P1 | Read data sampled only during valid transfer completion | apb_sanity_test | Read apb_mas_mon validation | CLOSE | 0.75 | CLOSE
APB_SCB_01 | Write Prediction | Verify apb_apb_scoreboard predicts write operations | apb_assertions | apb_assertions | P1 | apb_apb_scoreboard stores expected write transactions | apb_sanity_test | Prediction logic validation | CLOSE | 0.65 | CLOSE
APB_SCB_02 | Read Data Check | Verify apb_scoreboard compares expected and actual read data | apb_assertions, apb_mas_mon | apb_assertions | P1 | apb_scoreboard performs expected vs actual data comparison | apb_sanity_test | Data comparison validation | CLOSE | 0.7 | CLOSE
APB_SCB_03 | Transaction Integrity | Verify end-to-end transaction correctness | apb_assertions, apb_mas_mon | apb_assertions | P1 | apb_scoreboard validates protocol-level transaction consistency | apb_sanity_test | End-to-end validation | CLOSE | 0.6 | CLOSE
APB_COV_01 | Read/Write Coverage | Verify functional coverage for read/write operations | apb_mas_mon | apb_mas_mon | P2 | Covergroups sample read and write transaction types | apb_cov_test | Functional coverage | CLOSE | 0.5 | CLOSE
APB_COV_02 | Address Coverage | Verify address range coverage | apb_mas_mon | apb_mas_mon | P2 | Address bins implemented in coverage model | apb_cov_test | Address coverage collection | CLOSE | 0.5 | CLOSE
APB_COV_03 | Data Coverage | Verify data pattern coverage | apb_mas_mon | apb_mas_mon | P2 | Coverage bins for low/medium/high/random data patterns | apb_cov_test | Data coverage validation | CLOSE | 0.45 | CLOSE
APB_COV_04 | Wait-State Coverage | Verify wait-state cycle coverage | apb_mas_mon | apb_mas_mon | P2 | Coverage captures varying PREADY delay cycles | apb_cov_test | Wait-state coverage | CLOSE | 0 | CLOSE
APB_COV_05 | Cross Coverage | Verify cross coverage between operation/address/data | apb_mas_mon | apb_mas_mon | P2 | Cross bins implemented for transaction combinations | apb_cov_test | Cross coverage validation | CLOSE | 0 | CLOSE
APB_RAND_01 | Random Transaction Generation | Verify constrained-random APB transaction generation | apb_mas_drv | apb_mas_drv | P2 | Randomized sequence item generation using constraints | apb_random_test | CRV validation | CLOSE | 0.4 | CLOSE
APB_RAND_02 | Random Address Generation | Verify randomized address generation | apb_mas_drv | apb_mas_drv | P2 | Address randomized within valid address space | apb_random_test | Address randomization validation | CLOSE | 0.4 | CLOSE
APB_RAND_03 | Random Wait Injection | Verify randomized slave wait-state insertion | apb_mas_drv, apb_mas_mon | apb_mas_drv, apb_mas_mon | P2 | Random wait cycles introduced through PREADY control | apb_random_test | Random wait-state validation | CLOSE | 0 | CLOSE

## testcases
TEST NAME | DESCRIPTION | TESTCASE STEPS | PRIORITY | COMMENTS | IMPLEMENTATION STATUS
apb_reset_test | Verify APB reset behavior and recovery in the environment | 1) Assert reset on-the-fly during active transfers 2) Verify DUT memory clear 3) Verify correct resumption and recovery post-reset | P1 | Reset recovery validation | CLOSE
apb_random_test | Verify constrained-random APB transaction generation | 1) Enable randomized sequence generation 2) Generate random transfers 3) Verify legal protocol operation | P2 | Random stimulus validation | CLOSE
apb_sanity_test | Verify sanity of basic directed read and write transactions | 1) Generate directed write transaction 2) Drive setup/access phases 3) Generate directed read transaction 4) Verify read data matches write data | P1 | Sanity write/read verification | CLOSE
apb_boundary_test | Verify APB boundary address/data values | 1) Generate transactions with boundary address (0, ADDR_MAX) 2) Generate transactions with boundary data (0, DATA_MAX) 3) Verify boundary correctness | P2 | Boundary value validation | CLOSE
apb_transition_test | Verify write-to-read, read-to-write, write-to-write, read-to-read transitions | 1) Generate sequential transfers with transition kinds 2) Execute without idle cycle 3) Verify protocol continuity | P2 | Transition timing validation | CLOSE
apb_wr_rd_same_test | Verify write then read to the same address | 1) Write known data to an address 2) Immediately read same address 3) Compare expected and actual data | P1 | Read-after-write data integrity | CLOSE
apb_cov_test | Verify functional coverage collection | 1) Generate covergroup target scenarios 2) Sample coverage bins 3) Achieve maximum coverage | P2 | Coverage verification | CLOSE
apb_error_test | Verify PSLVERR error response handling | 1) Generate invalid transaction 2) Assert PSLVERR 3) apb_mas_mon error response 4) Verify transaction handling | P2 | Error handling verification | CLOSE

## assertions
ASSERTION ID | ASSERTION NAME | PROPERTY CHECKED | ASSERTION DESCRIPTION | PRIORITY | STATUS
APB_ASRT_01 | penable_psel_check | PENABLE to PSEL check | Verify that when PENABLE is asserted, PSEL is also asserted | P1 | CLOSE
APB_ASRT_02 | setup_to_access_check | Setup to Access transition | Verify that SETUP phase transitions to ACCESS phase in the next clock cycle | P1 | CLOSE
APB_ASRT_03 | p_addr_stable_wait | Address stability during wait | Verify that PADDR remains stable when PSEL and PENABLE are high and PREADY is low | P1 | CLOSE
APB_ASRT_04 | p_write_stable_wait | PWRITE stability during wait | Verify that PWRITE remains stable when PSEL and PENABLE are high and PREADY is low | P1 | CLOSE
APB_ASRT_05 | p_pwdata_stable_wait | PWDATA stability during wait | Verify that PWDATA remains stable during write wait states | P1 | CLOSE
APB_ASRT_06 | p_psel_hold_wait | PSEL hold during wait | Verify that PSEL remains high during wait states | P1 | CLOSE
APB_ASRT_07 | p_penable_hold_wait | PENABLE hold during wait | Verify that PENABLE remains high during wait states | P1 | CLOSE
APB_ASRT_08 | p_no_unknown_control | Unknown control check | Verify that critical APB control signals never contain X/Z values | P1 | CLOSE
APB_ASRT_09 | p_pslverr_valid | PSLVERR timing check | Verify that PSLVERR is only asserted when PSEL, PENABLE, and PREADY are high | P1 | CLOSE
APB_ASRT_10 | p_reset_behavior | Reset default signals | Verify that PSEL and PENABLE remain low during reset assertion | P1 | CLOSE
APB_ASRT_11 | p_access_after_setup | Access after setup check | Verify that ACCESS phase is preceded by a SETUP phase | P1 | CLOSE
APB_ASRT_12 | p_idle_state_valid | Idle state check | Verify that PENABLE is low when PSEL is low (IDLE state) | P1 | CLOSE
APB_ASRT_13 | p_pstrb_stable_wait | PSTRB stability check | Verify that PSTRB remains stable when PSEL and PENABLE are high and PREADY is low | P1 | CLOSE
APB_ASRT_14 | p_no_unknown_pstrb | Unknown PSTRB check | Verify that PSTRB contains no X/Z bits during active write transfer | P1 | CLOSE

## coverage
COVERAGE ID | COVER GROUP | COVERPOINT / CROSS | SAMPLING DESCRIPTION | STATUS
COV_01 | apb_transfer_cg | cp_kind | Sample read and write transfer types | CLOSE
COV_02 | apb_transfer_cg | cp_addr_region | Sample valid address regions (low, lowmid, highmid, high) | CLOSE
COV_03 | apb_transfer_cg | cp_addr_boundary | Sample first and last address boundaries | CLOSE
COV_04 | apb_transfer_cg | cp_kind_transition | Sample transaction transitions (WR->WR, WR->RD, RD->WR, RD->RD) | CLOSE
COV_05 | apb_transfer_cg | cp_wait_state | Sample varying wait-state cycles (0, 1, 3, 12) | CLOSE
COV_06 | apb_transfer_cg | cp_response | Sample error response checking (pslverr) | CLOSE
COV_07 | apb_transfer_cg | cross_kind_addr_region | Cross coverage between transaction kind and address region | CLOSE
COV_08 | apb_write_data_cg | cp_write_data | Sample write data quadrants (zero, low, mid, high, max) | CLOSE
COV_10 | apb_write_data_cg | cp_pstrb | Sample write strobe byte-lane configurations (all bytes, single byte, half word) | CLOSE
COV_09 | apb_read_data_cg | cp_read_data | Sample read data quadrants (zero, low, mid, high, max) | CLOSE